## Project Planner
Project Planner - Team 7
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 12 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1 | Discussing Meeting Dates | 4 | 1 | 4 | 1 | 100%
2 | Understanding Project Requirements | 4 | 2 | 4 | 2 | 100%
3 | Understand narrative from client Interview | 5 | 2 | 5 | 2 | 95%
4 | Identify what elements to be created | 5 | 1 | 5 | 1 | 80%
5 | Planning the design of the user interface | 5 | 2 | 5 | 2 | 90%
6 | Creating HTML,CSS and JavaScript files and figure out what needs to be done in each file | 6 | 3 | 6 | 3 | 50%
7 | Start coding | 6 | 4 | 6 | 4 | 0%
8 | Test code | 6 | 4 | 6 | 4 | 0%
9 | Identify errors in code and figure out how to correct it | 6 | 4 | 6 | 4 | 0%
10 | Final Testing of code | 10 | 1 | 10 | 1 | 0%
11 | Finalize Web App | 10 | 1 | 10 | 1 | 0%